## Planning Task Calendar
| Owner | Task | Completed? |  |  | Previous Year's Notes
Feb - April |  |  |  | Prep Work | Day/Week Of Work
| Committee Chair 1 | Secure location | FALSE
| Committee | Secure date | FALSE
| Committee Chair 1 | Secure Chefs | FALSE
| Committee Chair 2 | Secure wine | FALSE
| Committee | Set planning meetings | FALSE
| Committee | Assign Major Roles: | FALSE
| Committee Chair 1 | Lead Event Prep Coordinator | FALSE
| - | Chef & Ingredient Coordinator | FALSE
| - | Marketing & Registration Coordinator | FALSE
| Committee Chair 2 | On-Site Set Up Coordinator | FALSE | Create site plan with Committee Chair 1, optimize space, storage, and traffic patterns. | Organization of supplies while on site, informational assitance to volunteers, and general logistics during day before set-up.
A board member may take on more than one coordinator role if they have the time to commit. | Committee Chair 1 | Service Materials Coordinator | FALSE | Chief checklist manager! Plating, silverware, linens, tables, tents, chairs, ice chests, etc | Seeing that everything arrives onsite and gets returned!
| Volunteer 1 | Lighting Coordinator | FALSE | Lighting plans for all aspects of venue | Lighting set up and clean up lead
| Committee Member B | Music & Electricity Coordinator | FALSE | Musician communications & electricity needs planning | Generator & extension cord wizard! Assisting musicians with set up if needed.
| Committee Chair 2 | Auction Item Coordinator | FALSE | Locating, tracking, and storing of auction items | Set up of silent auction tables, distributing prizes to winners (with help of auction table cashier)
| Committee Member A | Auction Logistics Coordinator | FALSE | Creating & managing online auction & auction paperwork | Managing online auction, delivering silent auction forms to event location.
| Committee Member C | Gifts Coordinator | FALSE | Purchase, assemble thank you gifts for volunteers & chefs | Distributing gifts on day of or week after
| Committee Member D | Volunteer Coordinator | FALSE | Set volunteer plan, recruit volunteers & manager schedule, send volunteer reminder emails | Orient volunteers to all shifts (both prep, harvest, & day of)
| Volunteer 2 | Thanking Coordinator | FALSE | Plan for thanking, keep list of who to thank | Coordinate Thank you cards from board to chefs, volunteers, donors, in-kind donors, and auction winners
| Volunteer 3 | Generator Manager | FALSE | Pick up generator gas | Keeping tabs on gas in the generators during dinner
May |  |  | FALSE | 2022 Notes
| Committee | 1st Planning Meeting | FALSE
| Committee | Approve budget & set goals | FALSE
| Committee | Determine how many people | FALSE
| Committee | Go over Planning Spreadsheet, assign tab reviews | FALSE
| Committee Chair 1 | Review & Update Tab: Calendar | FALSE
| Committee Chair 2 | Review & Update Tab: Budget (Draft for 2nd meeting) | FALSE
| Committee Chair 2 | Review & Update Tab: Sponsor Tickets | FALSE
| Committee Chair 1 | Review & Update Tab: Supplies | FALSE
| Committee Chair 2 | Review & Update Tab: Event Timeline | FALSE
| Committee Chair 1 | Review & Update Tab: All Prep To-Do Lists | FALSE
| Committee Chair 2 | Review & Update Tab: Auction Items | FALSE
| Committee Chair 1 | Review & Update Tab: Who to Thank, Gifts & Donations Tracking | FALSE
| Committee Member B | Find volunteer artist for poster/social/website | FALSE
| Committee Chair 1 | Send out quick email & Social Media Save-the-Date to full list, include farmers & previous attendees | FALSE
| Committee Chair 2 | Finalize Chefs & Course Assignments | FALSE
| Committee Chair 1 | Start Locating supplies | FALSE
| Committee Chair 1 | Locate Tables and Chairs | FALSE
| Committee Chair 1 | Schedule Servingware pick up and return | FALSE
| Committee Chair 1 | Schedule Linen Rental | FALSE
| Committee Chair 1 | Secure Lead Servers & Expo | FALSE
| Committee Chair 1 | Reserve Uhaul(s) | FALSE
| Committee Member D | Set Volunteer Plan (Board, Movers & Servers) | FALSE
| Committee Member B | Book Musicians | FALSE
| Committee Chair 2 | Schedule a Menu Meeting in June on-site with Chefs & lead servers | FALSE
| Committee Chair 2 | Check in with vintner(s) re: numbers & pairing | FALSE
| Committee Chair 2 | Start collecting auction items | FALSE
| Committee Chair 2 | Appeal to board members for assist in soliciting auction items | FALSE
| Committee Chair 1 | Update Web Page on CCM Site | FALSE
| Committee Chair 1 | Ticketing and registration set up | FALSE
| Committee Chair 1 | Create List of Print Materials Needed | FALSE
| Committee Chair 2 | Buy insurance and banquet permit | FALSE
FALSE
June |  |  | FALSE
| Committee Chair 1 | Open ticket sales to Sponsors only for 2 weeks | FALSE
| Committee Chair 1 | Draft Site Plan & Service Plan | FALSE
| Committee Chair 1 | Send Chef Wishlist Reminder Email | FALSE
June 15th, 11am | Committee Chair 2 | Host Menu/Service Meeting - Include service leads & expo | FALSE
| Committee Chair 2 | Update Menu & Ingredients Tabs of Spreadsheet | FALSE
| Committee | Determine poster design & Small Invite Design | FALSE
| Committee | Thank you card design | FALSE
| Committee Chair 1 | Print Posters & TY/Invite Cards | FALSE
| Committee Chair 2 | Create Farm to Table blurb for advertising | FALSE
| Committee Chair 2 | Go over De-brief from previous year | FALSE
14-16 | Committee Chair 1 | Launch ticket sales*** & Start Raffle | FALSE
| Committee Chair 2 | Line up photographer | FALSE
| Committee | Have individual board members create invite lists at Board Meeting | FALSE
| Committee Chair 1 | Include in newsletter update | FALSE
| Committee Chair 1 | Send out a direct email invitation to previous attendees on June 30th | FALSE
| Committee | Post Posters | FALSE
| Committee Chair 1 | Have posters at the market | FALSE
| Committee | Where else can we advertise? | FALSE
| Committee Chair 1 | Back up plan for weather | FALSE
| Committee Chair 1 | Reminder email to Chefs for Wishlists & Menu Details | FALSE
| Committee Chair 1 | Check in with Farmers about produce from wishlists | FALSE
| Committee Chair 2 | Set up coffee donation | FALSE
July |  |  | FALSE
| Committee Member D | Send initial Volunteer Email | FALSE
| Committee Chair 1 | Coordinate all supplies | FALSE
| Committee Chair 1 & Committee Chair 2 | Site Visit to design and finalize event Layout | FALSE
| Committee Chair 1 | Check in with Chefs re: menus | FALSE
| Committee Chair 2 | Who will run the payment recordkeeping RSVP list | FALSE
| Committee Member D | Update volunteer spreadsheet | FALSE
| Committee Member D | Other volunteers for set-up, take-down | FALSE
| Committee Member D | Volunteers for bussing/dishwashing | FALSE
| Committee Chair 1 | Reserve port-a-toilets | FALSE
| Committee Chair 1 | Have needed items list for Board Meeting | FALSE
| Committee Chair 1 | Create Event Menu & Program | FALSE
| Committee | Board to f/u with phone calls and emails for invites | FALSE
| Committee Chair 1 | Send out another email invitation/reminder on July 30th | FALSE
| Committee Chair 1 | Confirm rented supplies list | FALSE
| Committee Chair 1 | Finalize Linen order | FALSE
| Committee | Get other advertisements opportunities | FALSE
| Committee Chair 1 | Create week of, day of timeline | FALSE
| Committee Chair 1 | Track Sponsor Reservations | FALSE
| Committee Chair 1 | Plan for guest gifts - dried arrangements | FALSE
| Committee Member C | Get the volunteer & chefs TY gifts together | FALSE
| Volunteer 1 | Make sure we have what we need for lighting | FALSE
| Committee | Assign board volunteer roles | FALSE
| Committee Chair 1 | Check for any missing supplies | FALSE
| Committee Chair 1 | FB Shout Outs to: | FALSE
| Committee Chair 1 | Sponsors | FALSE
| Committee Chair 1 | chefs and vendors | FALSE
| Committee Chair 1 | musicians | FALSE
| Committee Member D | Line up Volunteer drinks and dinner | FALSE
| Committee Member C | Buy thank you gifts for farmers & chefs | FALSE
| Volunteer 1 | Get lights for around tables and walkway | FALSE
| Committee Chair 1 | Consistent communication with farmers to ask for specific food donations to the event | FALSE
August |  |  | FALSE | 2022 Notes
| Committee | Any final push for buying tickets? | FALSE
| Committee Chair 2 | Finalize Silent Auction Items | FALSE
| Committee Member A | Make Auction Descriptions in Canva | FALSE
| Committee Member A | Create silent auction bid sheets/gift certs | FALSE
| Committee Chair 1 | Check on dishwashing station supplies | FALSE
| Committee Chair 1 | Finalize & Print Event program & Menus | FALSE
| Committee Chair 1 | Create event signage | FALSE
| Committee Chair 1 | 1 week before event, email attendees.. mention clothing, parking | FALSE
| Committee Chair 1 | Email closer to F2T to inform people that they can donate @ event | FALSE
| Committee Chair 2 | Touch bases on the plan with Photographer | FALSE
| Committee Chair 1 | Check in with Sponsors who have not RSVP'd | FALSE
| Committee | Outline Speeches | FALSE
| Committee Chair 1 | Talk to 'asker' about the ask | FALSE
| Committee Chair 1 | Final Chef Emails - dietary restriction counts and menu verbage draft | FALSE
| Committee Member D | Buy extra food/drink items | FALSE
| Committee Chair 1 | Final reminders to our guests via email | FALSE
| Committee Member A | Print out silent aution bidding sheets & description sheets | FALSE
| Committee Chair 1 | Check the week of and day of timelines | FALSE
| Volunteer 2 | Create thanking system for after the event | FALSE
| Volunteer 2 | Get thank you notes together | FALSE
| Committee Member D & Committee Chair 1 | Get TY notes together for all the volunteers | FALSE
Late August | All | EVENT DAY | FALSE
FALSE
September |  |  | FALSE
| Committee Chair 2 | Record keeping from the event | FALSE
| Committee Chair 2 | Add all additional donor info to Spreadsheet | FALSE
| Volunteer 2 | TY's | FALSE
| Committee | De-brief and suggestions for Next Year | FALSE
FALSE
FALSE
FALSE
FALSE

## Planning Tasks by Coordinator
(Unassigned Tasks) | Committee | Done? | Committee Chair 1 | Done? | Committee Chair 2 | Done? | Committee Member A | Done? | Committee Member B | Done? | Committee Member C | Done? | Committee Member D | Done? | Volunteer 1 | Done? | Volunteer 2 | Done?
| Secure date | FALSE | Secure location | FALSE | Secure wine | FALSE | Auction Logistics Coordinator | FALSE | Music & Electricity Coordinator | FALSE | Gifts Coordinator | FALSE | Volunteer Coordinator | FALSE | Lighting Coordinator | FALSE | Thanking Coordinator | FALSE
| Set planning meetings | FALSE | Secure Chefs | FALSE | On-Site Set Up Coordinator | FALSE | Make Auction Descriptions in Canva | FALSE | Find volunteer artist for poster/social/website | FALSE | Get the volunteer & chefs TY gifts together | FALSE | Set Volunteer Plan (Board, Movers & Servers) | FALSE | Make sure we have what we need for lighting | FALSE | Create thanking system for after the event | FALSE
| Assign Major Roles: | FALSE | Lead Event Prep Coordinator | FALSE | Auction Item Coordinator | FALSE | Create silent auction bid sheets/gift certs | FALSE | Book Musicians | FALSE | Buy thank you gifts for farmers & chefs | FALSE | Send initial Volunteer Email | FALSE | Get lights for around tables and walkway | FALSE | Get thank you notes together | FALSE
| 1st Planning Meeting | FALSE | Service Materials Coordinator | FALSE | Review & Update Tab: Budget (Draft for 2nd meeting) | FALSE | Print out silent aution bidding sheets & description sheets | FALSE |  | FALSE |  | FALSE | Update volunteer spreadsheet | FALSE |  | FALSE | TY's | FALSE
| Approve budget & set goals | FALSE | Review & Update Tab: Calendar | FALSE | Review & Update Tab: Sponsor Tickets | FALSE |  | FALSE |  | FALSE |  | FALSE | Other volunteers for set-up, take-down | FALSE |  | FALSE |  | FALSE
| Determine how many people | FALSE | Review & Update Tab: Supplies | FALSE | Review & Update Tab: Event Timeline | FALSE | [6 empty] | Volunteers for bussing/dishwashing
| Go over Planning Spreadsheet, assign tab reviews | FALSE | Review & Update Tab: All Prep To-Do Lists | FALSE | Review & Update Tab: Auction Items | FALSE | [6 empty] | Line up Volunteer drinks and dinner
| Determine poster design & Small Invite Design | FALSE | Review & Update Tab: Who to Thank, Gifts & Donations Tracking | FALSE | Finalize Chefs & Course Assignments | FALSE | [6 empty] | Buy extra food/drink items
| Thank you card design | FALSE | Send out quick email & Social Media Save-the-Date to full list, include farmers & previous attendees | FALSE | Schedule a Menu Meeting in June on-site with Chefs & lead servers | FALSE
| Have individual board members create invite lists at Board Meeting | FALSE | Start Locating supplies | FALSE | Check in with vintner(s) re: numbers & pairing | FALSE
| Post Posters | FALSE | Locate Tables and Chairs | FALSE | Start collecting auction items | FALSE
| Where else can we advertise? | FALSE | Schedule Servingware pick up and return | FALSE | Appeal to board members for assist in soliciting auction items | FALSE
| Board to f/u with phone calls and emails for invites | FALSE | Schedule Linen Rental | FALSE | Buy insurance and banquet permit | FALSE
| Get other advertisements opportunities | FALSE | Secure Lead Servers & Expo | FALSE | Host Menu/Service Meeting - Include service leads & expo | FALSE
| Assign board volunteer roles | FALSE | Reserve Uhaul(s) | FALSE | Update Menu & Ingredients Tabs of Spreadsheet | FALSE
| Any final push for buying tickets? | FALSE | Update Web Page on CCM Site | FALSE | Create Farm to Table blurb for advertising | FALSE
| Outline Speeches | FALSE | Ticketing and registration set up | FALSE | Go over De-brief from previous year | FALSE
| De-brief and suggestions for Next Year | FALSE | Create List of Print Materials Needed | FALSE | Line up photographer | FALSE
|  |  | Open ticket sales to Sponsors only for 2 weeks | FALSE | Set up coffee donation | FALSE
|  |  | Draft Site Plan & Service Plan | FALSE | Who will run the payment recordkeeping RSVP list | FALSE
|  |  | Send Chef Wishlist Reminder Email | FALSE | Finalize Silent Auction Items | FALSE
|  |  | Print Posters & TY/Invite Cards | FALSE | Touch bases on the plan with Photographer | FALSE
|  |  | Launch ticket sales*** & Start Raffle | FALSE | Record keeping from the event | FALSE
|  |  | Include in newsletter update | FALSE | Add all additional donor info to Spreadsheet | FALSE
|  |  | Send out a direct email invitation to previous attendees on June 30th | FALSE
|  |  | Have posters at the market | FALSE
|  |  | Back up plan for weather | FALSE
|  |  | Reminder email to Chefs for Wishlists & Menu Details | FALSE
|  |  | Check in with Farmers about produce from wishlists | FALSE
|  |  | Coordinate all supplies | FALSE
|  |  | Check in with Chefs re: menus | FALSE
|  |  | Reserve port-a-toilets | FALSE
|  |  | Have needed items list for Board Meeting | FALSE
|  |  | Create Event Menu & Program | FALSE
|  |  | Send out another email invitation/reminder on July 30th | FALSE
|  |  | Confirm rented supplies list | FALSE
|  |  | Finalize Linen order | FALSE
|  |  | Create week of, day of timeline | FALSE
|  |  | Track Sponsor Reservations | FALSE
|  |  | Plan for guest gifts - dried arrangements | FALSE
|  |  | Check for any missing supplies | FALSE
|  |  | FB Shout Outs to: | FALSE
|  |  | Sponsors | FALSE
|  |  | chefs and vendors | FALSE
|  |  | musicians | FALSE
|  |  | Consistent communication with farmers to ask for specific food donations to the event | FALSE
|  |  | Check on dishwashing station supplies | FALSE
|  |  | Finalize & Print Event program & Menus | FALSE
|  |  | Create event signage | FALSE
|  |  | 1 week before event, email attendees.. mention clothing, parking | FALSE
|  |  | Email closer to F2T to inform people that they can donate @ event | FALSE
|  |  | Check in with Sponsors who have not RSVP'd | FALSE
|  |  | Talk to 'asker' about the ask | FALSE
|  |  | Final Chef Emails - dietary restriction counts and menu verbage draft | FALSE
|  |  | Final reminders to our guests via email | FALSE
|  |  | Check the week of and day of timelines | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Budget
Expenses | Item | Previous Year's Actuals | Budget | Notes
Admin & Services
Printing (Poster, Menus)
Insurance
Special Occasion License
Linens Rental
Servingware Rental
PortaPotty Rental
Uhaul + Gas
Employee Vehicle Use
Photographer
Staff Wages
Other - Equipment Purchased
| ADMIN & SERVICE EXPENSES | 0 | 0
Food
Farm Purchases & Chef Reimbursements
Flowers (Centerpieces, etc)
Meat/Main Dish Protein
Pizza & Beverages for Volunteers
Champagne
Ice
| FOOD EXPENSES | 0 | 0
Music | Riverdog Shakedown
Rib + Corbin
| MUSIC EXPENSES | 0 | 0
Gifts
Location Host
Chefs (6 of them)
Volunteers (20 of them)
Any other donors need gifts?
| GIFT EXPENSES SUBTOTAL | 0 | 0
| EXPENSES TOTAL | 0 | 0
Income
Ticket Sales
Direct Donations
Auction
| GROSS INCOME | 0 | 0
| NET INCOME | 0 | 0

## Ticketing Sponsors
Sponsor | Email | Promo Code | Number of Tickets | Code Sent | Redeemed? | Redeemed By Who?
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
|  |  |  | FALSE | FALSE
Total Tickets: |  |  | 0

## Ticketing Needs to Register
Date | Name | Email Address | Number of Tickets | Paid Via | Received code? | Registered
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## Ticketing Waitlist
Name | Number of Tickets | Emailed | Must Redeem by: | Redeemed?

## Supplies
Item Coordinator/ Location | Supplies Needed | Quantity Needed | Quantity Acquired | READY | Provided By | Notes
General
Market Storage | Tents |  |  | FALSE
| Back Up tent |  |  | FALSE
Rental Company | Back up event tent |  |  | FALSE
| Ice chests |  |  | FALSE
| Ice |  |  | FALSE
Market Storage | Beverage Coolers |  |  | FALSE
| Grill |  |  | FALSE
Market Storage | Blue Masking tape to lable folks items |  |  | FALSE
Market Storage | 8 0z shallow Mason :Jars for tea lights |  |  | FALSE
Market Storage | Vases |  |  | FALSE
Market Storage | Extension cords |  |  | FALSE
| 10 ft tposts |  |  | FALSE
FALSE
FALSE
| Lighting |  |  | FALSE
| Lights for walking to bathrooms |  |  | FALSE
| Spotlights for Kitchen |  |  | FALSE
Market Storage | LED tea lights |  |  | FALSE
| Hanging/string lights for the market table, auction, & wine tables |  |  | FALSE
| String lights for chefs |  |  | FALSE
| String lights for dining area |  |  | FALSE
FALSE
| Flowers |  |  | FALSE
| Centerpiece arrangements |  |  | FALSE
| Place Setting Flower Arrangements |  |  | FALSE
| Lavender for champaign flutes and place settings |  |  | FALSE
FALSE
| Dining Room |  |  | FALSE
| Tables |  |  | FALSE
Rental Company | 8-top rounds |  |  | FALSE
Rental Company | 6ft Rectangle |  |  | FALSE
Rental Company | Bistro Tables |  |  | FALSE
Market Storage | 6ft Rectangle |  |  | FALSE
Rental Company | 6ft Rectangle |  |  | FALSE
Rental Company | 6-top Round |  |  | FALSE
Market Storage | 4' Table |  |  | FALSE
Rental Company | Chairs |  |  | FALSE
Rental Company | Back up tables |  |  | FALSE
Rental Company | Champagne Flutes |  |  | FALSE
Rental Company | Wine glasses |  |  | FALSE
Rental Company | Water glasses |  |  | FALSE
Rental Company | Beer Glasses |  |  | FALSE
| Dinnerware |  |  | FALSE
Rental Company | C1 Plates |  |  | FALSE
Rental Company | C2 Bowls |  |  | FALSE
Rental Company | C3 Plates |  |  | FALSE
Market Storage | C4: Sorbet Jars (4 oz) |  |  | FALSE
Rental Company | C5: Dinner Plates |  |  | FALSE
Market Storage | C6: Dessert Jars (8oz) |  |  | FALSE
Market Storage | Fork/knife resting small plate |  |  | FALSE
| Flatware |  |  | FALSE
Rental Company | Dinner Forks |  |  | FALSE
Rental Company | Dinner Knives |  |  | FALSE
Rental Company | Soup Spoons |  |  | FALSE
Rental Company | Intermezzo Spoons |  |  | FALSE
| Dessert Spoons |  |  | FALSE
Market Storage | Salt and Pepper shakers |  |  | FALSE
| Coffee cups and saucers |  |  | FALSE
| Linens |  |  | FALSE
| 8ft Round White for Dining Tables |  |  | FALSE
| 6ft Rectangle Black for Kitchen & bar |  |  | FALSE
| 6ft white round |  |  | FALSE
| Napkins - mustard |  |  | FALSE
| Napkins - black |  |  | FALSE
| Greeting Table |  |  | FALSE
Market Storage | Table Runners |  |  | FALSE
FALSE
| Service & Servers |  |  | FALSE
Rental Company | Water pitchers |  |  | FALSE
Rental Company | Bus Bins |  |  | FALSE
Market Storage | Bar Towels |  |  | FALSE
Rental Company | Service Trays |  |  | FALSE
Rental Company | Tray stands for servers |  |  | FALSE
FALSE
| Beer - mini keg |  |  | FALSE
| Beer - Pony Keg Alpenhaze |  |  | FALSE
| Champaign/Brut |  |  | FALSE
| Cream and Sugar Service |  |  | FALSE
FALSE
| Kitchen |  |  | FALSE
| Dishwashing stuff |  |  | FALSE
Market Storage | Garbage Bins |  |  | FALSE
Market Storage | Garbage Bins for Kegs |  |  | FALSE
Market Storage | Recycling Bin for Bar |  |  | FALSE
| Compost Totes |  |  | FALSE
Market Storage | Hand Washing Setups |  |  | FALSE
FALSE
| Print Matierals |  |  | FALSE
Committee Chair 1 | Folding Cards with artwork for Thank Yous |  |  | FALSE
| Posters |  |  | FALSE
| Paper for Menus and Signage |  |  | FALSE
Committee Chair 1 | Menus |  |  | FALSE
| Event Signage |  |  | FALSE
Market Storage | Check In Here A-Board |  |  | FALSE
Market Storage | Table Signs (W/server name & QR Code) |  |  | FALSE
Market Storage | Restrooms This Way |  |  | FALSE
Market Storage | Glassware Drop |  |  | FALSE
| Reception Appetizer Decription Sign |  |  | FALSE
| Reception Champagn Sign |  |  | FALSE
| Reception Elixir Sign |  |  | FALSE
| Reserved signs |  |  | FALSE
| Volunteers list with contacts |  |  | FALSE
| Event Timelines - 4 copies |  |  | FALSE
| Talking Points & Timelines for Speakers |  |  | FALSE
| Auction Bid Sheets |  |  | FALSE
| Auction Frames |  |  | FALSE
| Auction Descriptions |  |  | FALSE
| Donation SpreadSheet |  |  | FALSE
FALSE

## Supplies By Coordinator
Rental Company | Market Storage | Committee Chair 1 | Committee Chair 2 | Committee Chair 2 | Committee Member B | Volunteer 2 | Volunteer 1 | Committee Member A | Roots
Back up event tent | Tents | Folding Cards with artwork for Thank Yous | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8-top rounds | Beverage Coolers | Menus
6ft Rectangle | Blue Masking tape to lable folks items
Bistro Tables | 8 0z shallow Mason :Jars for tea lights
6ft Rectangle | Vases
6-top Round | Extension cords
Chairs | LED tea lights
Back up tables | 6ft Rectangle
Champagne Flutes | 4' Table
Wine glasses | C4: Sorbet Jars (4 oz)
Water glasses | C6: Dessert Jars (8oz)
Beer Glasses | Fork/knife resting small plate
C1 Plates | Salt and Pepper shakers
C2 Bowls | Table Runners
C3 Plates | Bar Towels
C5: Dinner Plates | Garbage Bins
Dinner Forks | Garbage Bins for Kegs
Dinner Knives | Recycling Bin for Bar
Soup Spoons | Hand Washing Setups
Intermezzo Spoons | Check In Here A-Board
Water pitchers | Table Signs (W/server name & QR Code)
Bus Bins | Restrooms This Way
Service Trays | Glassware Drop
Tray stands for servers

## Menu and Ingredients
Course | Delivered | Food/Item | Quantity | Delivery Notes | Donor/Vendor | Business | Chef/Contact | Phone Number | Email Address | Cost Paid | Donated Value | Contact** | Who is picking up? | Picked up | Delivered to Chefs | Notes***
White Wine
Red Wine | [5 empty] | Plain Cellars
Beer (Keg) | [5 empty] | Bushel & Bee | Kayla Applebay
Bubbles
Thursday |  | Saturday | Sunday
#N/A |  | #N/A | #N/A

## Grab List
Day Of | Day Before
Head lamps | Donation envelopes
Lavender | Pens
Banquet permit
Sign in sheet | Sponsor banner
Signage | Market Chalboards
Extra tables
Credit Card Machine & Charger | Bar Rags
Candles | Large Jars
Candle jars
More pens | 4oz jars
Bar rags | manila envelope for donations
Auction Frames
Spotlights
Candle dishes
Jars

## Gifts
Recipients | Gift | Cost

## Board Volunteer Shifts
Board & Staff Volunteer Shifts | Board Members | Times | Tasks
3 Days Before
Drop off Vases to Angela |  | AM
Trim trees back from kitchen tents |  | AM
Meet port-a-potty drop off |  | AM
2 Days Before
Market Trailer Delivery
Dishwashing setup delivery
Ice Chest Pickup & Delivery
Accessory Needs? |  | Monday
Linen Pickup |  | Monday AM or Sunday
Generator Pickup form Lauren |  | Monday AM or Sunday
Generator Delivery |  | Sunday
Day Before
Finalizing Lights |  | 8:00
Uhaul Pickup |  | 7:30
Mowing the lawn |  | 10-11am
Uhaul Team (Driver) |  | 8am-12pm | Pick up at: Ravenous, Beecher & Tierra
Uhaul Team |  | 8am-12pm | Pick up at: Ravenous, Beecher & Tierra
Uhaul Team |  | 8am-12pm | Pick up at: Ravenous, Beecher & Tierra
Delivering Tomatoes to Marci |  | 11:00 | Pick up from Snowgrass
On-site Coordinator |  | 11am-4pm
Cut Flower Pickup (unless being delivered) |  | AM
On-site set up |  | 12pm-2pm | Setting up tents, tables & chairs; Staging Dishware; Posting Signage
On-site set up |  | 12pm-2pm | Setting up tents, tables & chairs; Staging Dishware; Posting Signage
On-site set up |  | 12pm-4pm | Setting up tents, tables & chairs; Staging Dishware; Posting Signage
On-site set up |  | 12pm-4pm | Setting up tents, tables & chairs; Staging Dishware; Posting Signage
On-site set up |  | 12pm-4pm | Setting up tents, tables & chairs; Staging Dishware; Posting Signage
Ice Chest Filling |  | 16:00
Compost Bin Delivery
Available in the Evening |  | After 5
Day Of
On-Site Coordinator |  | 2022-12-03
Final Dining Room Decor/Kitchen set-up |  | 1-3pm | Tablecloths & decor
Final Dining Room Decor/Kitchen set-up |  | 1-3pm | Tablecloths & decor
Final Dining Room Decor/Kitchen set-up |  | 1-3pm | Tablecloths & decor
Water Jug Filling |  | 13:00
Projector Set up |  | 1:00
Auction Item Setup |  | 2022-12-01
Auction Item Setup |  | 2022-12-01
Volunteer Room Setup |  | 14:00 | drinks, paper plates & napkins, trash can, volunteer gifts
Pizza Pickup |  | 16:00
Generator Guru |  | 2022-05-10
Hosting the Check-In Table |  | 4:30-6
Hosting the Check-In Table |  | 2022-05-06
Assisting with Auction |  | 8pm-9pm
Assisting with Auction |  | 8pm-9pm | Payment Manager
Handing out Chef Gifts |  | 21:00
Compost & Garbage Disposal
Packing down for the night |  | 9-10pm | Scraping extra dishes, collecting table cloths and decor, folding & loading tables, folding chairs, staging for uhaul
Day After
Packing Up Uhaul & Trailer |  | 9am-12pm | Tents, lights, power cords,
Packing Up Uhaul & Trailer |  | 9am-12pm
Packing Up Uhaul & Trailer |  | 9am-12pm
Packing Up Uhaul & Trailer |  | 9am-12pm
Uhaul Team Lead (Driver) |  | 12-4pm
Uhaul Team |  | 12-4pm
Uhaul Team |  | 12-4pm
Final Dish-Washing at Ravenous |  | 5:00
Final Dish-Washing at Ravenous |  | 5:00

## Volunteers
Confirmed Vounteers | [7 empty] | Previous volunteers
Role | Name | Confirmed? | Contacted by: | Contact Info | Address | Thank you sent/delivered | Survey Link Sent |  | hannahlricer@gmail.com
Expo |  | FALSE | [6 empty] | eleanorleeclarke@gmail.com
Server 1 (Table 1 & 2) |  | FALSE | [6 empty] | caroline@eathikelove.com
Server 2 (Table 3 & 4) |  | FALSE | [6 empty] | csianna14@gmail.com
Server 3 (Table 5 & 6) |  | FALSE | [6 empty] | egrlily22@gmail.com
Server 4 (Table 7 & 8) |  | FALSE | [6 empty] | ivyspiegost@icloud.com
Server 5 (Table 9 |  | FALSE | [6 empty] | jschluck21@gmail.com
Server 6 (Table 10 |  | FALSE | [6 empty] | elisabethkeziah@gmail.com
Server 7 (Table 11 |  | FALSE | [6 empty] | tatumresources@msn.com
Server 8 (Table 12 |  | FALSE | [6 empty] | tatumresources@msn.com
Server 9 Table 13 |  | FALSE | [6 empty] | maxtrieger@yahoo.com
Server 10 Table 14 & 15 |  | FALSE | [6 empty] | nora.b.heath@gmail.com
Floater |  | FALSE
Floater |  | FALSE
Floater |  | FALSE | [6 empty] | snowgrassfarm@gmail.com
Floater (arriving at 4:30-5) |  | FALSE | [6 empty] | mia.fehl@munchenhaus.com
Floater (arriving at 4:30-5) |  | FALSE | [6 empty] | rachel.booher@iciclebrewing.com
Dish Washer |  | FALSE | [6 empty] | ryan@viscontis.com
Dish Washer |  | FALSE | [6 empty] | kayla@bushelandbee.com
Lead Dish Washer |  | FALSE | [6 empty] | tpreston@rhleavenworth.com
Bev Table Host - Beer & Elixirs |  | FALSE | [6 empty] | dahlsn@gmail.com
Backup Server |  | FALSE
Backup Server |  | FALSE
Backup Server |  | FALSE
Wine Server |  | FALSE | [6 empty] | saltandhoneycooking@gmail.com
Wine Server |  | FALSE | [6 empty] | yodelinbroth@gmail.com
Wine Server |  | FALSE | [6 empty] | sullavita931@gmail.com
Wine Server |  | FALSE
Wine Server |  | FALSE
|  | FALSE | [6 empty] | troy@leavenworth.org
FALSE
FALSE
FALSE
FALSE

## Server Orientation Content
Note cards for servers!
Servers each have 1 or 2 tables - Assign who has 2 tables
Please select your table(s) and write your name on the centerpiece
Wine Servers - 4 walk the floor (assign each a section), others stay at the bar to open bottles & pour beer/elixirs
Floaters will walk the floor refilling waters & help run food
Before Service:
Servers Set the tables with Fork, Knife, Soup Spoon, Intermezzo Spoon, Napkin, Water glass, Wine Glass, Menu & micro-bouquet- show table setting
Floaters - Fill water glasses
Pizza dinner @ 4:30, then back to the floor by 5:15
Service Flow:
As guests arrive to the floor, servers will tell them to select a table and wine servers will walk the floor with wine bottles
Floaters, take empty champagn flutes to dish pit
**Announcement to take your seats from Rob & Committee Chair 1**
Servers will greet their tables, introduce yourself and first ask if anyone has any dietary restrictions
Take notes on Dietary Restrictions and return them to Gabby
Ask if you can get anyone a drink other than wine - Elixirs and beer options are listed at the bottom of the menu
Fetch any drinks other than wine from the bar
Wine servers continue to walk the floor offering wine
**First Course is Announced**
Always bring dietary restriction plates to your table first (check this with Gabby)
Drop first course, check on everyone's drink
Clear plates as they empty - LEAVE FORKS & KNIVES - Scrape Plates in Dish Drop
**Second Course is Announced**
Drop second course, check on everyone's drinks
Clear bowls as they empty - take soup spoons & leave forks/knives - scrape bowls at dish drop
**Third Course is Announced**
Drop third course, check everyone's drinks
Clear plates as they empty - LEAVE FORKS & KNIVES - Scrape Plates in Dish Drop
**Intermezzo is announced**
Drop intermezzo, check everyone's drinks
Clear jars as they empty - take intermezzo spoons & leave forks/knives - scrape jars at dish drop
**Entree is announcced**
Drop Entree, check everyone's drinks
Clear plates as they emply and this time, TAKE ALL SILVERWARE - scrape plates at dish drop
Bring out Dessert Spoons
**Dessert is announced**
Drop desserts, final drink check
Clear dessert jars & spoons - scrape jars at dish drop

## Event Timeline
Day | Time | Event | Details
| AM | Micro-bouquets delivered
| 0.5 | Volunteer Room all set with: drinks, paper plates & napkins, trash can, volunteer gifts
| 0.5 | Initial Auction Setup
| 1-3pm | Volunteer Shift | Tablecloths out, all decor out, all signs out
| 0.54167 | Fill Water Jugs & Pitchers
| 0.5 | Set Up Tables w/linen, centerpieces | Double check all tables, chairs, lights, plates, etc were delivered , are clean, and ready for use
| 0.58333 | Start setting up the last minute items. See set up list.
| 0.625 | Keg & volunteer beverages delivery
| 0.625 | Chefs Arrive
| 0.625 | Board volunteers get changed
| 0.66667 | Photographer arrivers
| 0.66667 | Pizza pick up | Volunteer 2
| 0.66667 | All Servers Arrive (Volunteers & Wine Staff) | Committee Chair 1 gives server orientation, place settings out, final dining room touches - Names on centerpiece signs
| 0.66667 | Silent Auction finishing touches | Committee Chair 2,
| 0.66667 | Musicians & Music Coordinator arrive | Committee Member B orients Musicians
| 0.6875 | Volunteer & Band Pizza Dinner | In the house
| 0.1875 | Check-in Hosts Arrive | Committee Chair 1 orients Committee Member B on check in
| 0.70833 | Guests can arrive | Committee Members A & B at Check in Table
| 0.21875 | All servers to the floor
| 0.71875 | 1st Tour | first tour, drinks in hand, with host 1
| 0.72917 | 2nd Tour | second tour with host 2
| 0.73958 | Final check in | Call anyone who hasn't checked in, set out greeting sign for any stragglers: "Please join us down the path to your right"
| 0.74653 | Get everyone seated | Greetings and get seated, introduces Committee Chair 1
| 0.75 | Welcome | Committee Chair 1 Welcome (thank everyone, tell them what they're in for)
| 0.75347 | First Appetizer Served | CHEF introduces course 1
| 0.75694 | Music Starts
| 0.77083 | Soup Served | CHEF introduces course 2, Pass mic to Committee Member B
| 0.27431 | Sponsor and Event support recognition | Committee Member B
| 0.78819 | Tomato Salad Served | CHEF introduces Course 3
| 7:20-7:50PM | Music Intermission
| 0.80556 | intermezzo Served | CHEF shares about the Intermezzo, introduces Jenny
| 0.80903 | The ask! | Farmer speech - including how to donate online or with remit envelopes!
| 0.31944 | Bring it home - how to donate | "Bring it home" on ask donations and stoke the auction energy
| 0.32292 | Entree Served | CHEF introduces entree
| 0.32639 | Riverdog Resumes
| 0.34375 | Auction Closes
| 0.34375 | Compile Auction announcement list | Committee Chair 1 & Committee Chair 2
| 0.84722 | Dessert is served | CHEF introduces dessert
| 0.85069 | Auction winners announced / payment available/ auction items boxed for pick up | Announce Auction winners, thank you to all, get up and dance, and good night!
| 0.86458 | Collect all donation envelopes | Funnel them all back to Committee Member B to be sealed until counted/processed
| 0.89583 | Music ends (unless encore is demanded) | Clean up begins
| 0.89583 | Clean up - Litter, Linens, collect all dishware. drop the tables & chairs for reload. | Service volunteers, board members, other volunteers present
Day after event | 9am-12pm | Volunteer Shift
| 12-4pm | Return all picked up items and Uhaul

## Tasklist Week Of
Item | Date
Compost Tote Delivery
Board Work Party at Roots?
Check in with muscian
Check in with Chefs
Check in with Eagle Creek
Check in with photographer
Print sign in sheet
Print event signage
Pack up day of items
Check in with the 'asker'
Send final guest reminder email
Make sure Dan and Becky have the outline
Set up TY email for Thursday
Make sure thanking system is in place
Day before set up party
Make Board Member Boutonierres
Make Dietary Restriction Arrangements
Fill water jugs
Bring and set up farmers market tents
Pick flowers
Create Flower Decor in Mason jars
Post on FB
Day of set up
Volunteer food!
Volunteer beverages
Ice run
Event happens!
Clean up
Count money
Anything leftover that needs to be delivered
Email out to the Board
Debrief
Financials and Thanking

## Task List Day Before
Day Before Set Up
Action | Done?
T Posts
Clean wine glasses (most likely just a lite wet rag or cotten polishing)
Lights over dinner tables*****add lights
Lights and tents over table for chefs
Make sure we'll have proper signage for parking and restrooms
Count all plates & glassware & compare to expected counts
Plates under kitchen tables, sectioned out
Post signage for dish counts/index cards on each crate
Set up market banner - not this year
Set up hand wash station by bathrooms
wine and app tables at top and bottom
Set up reception bar & check in table
dining tables out
Chairs out
water all filled
Do we have all utensils and table settings ready for tomorrow?
generators an electrical
trash cans and trash bags
Solar Lights out

## Task List Day Of
Action | Items | Who
final light check
Parking signage
Bathroom signage
Fill Water Pitchers & Jugs
Ice Pick up
Polish all glassware & silverware
Reception Area table Decor | Table cloth, flowers, platters, napkins, labels
Set up Auction Items
Sign in table | Sign in sheets and pens
Table decor | table cloths, burlap runners, flower, lights
Remit envelopes to Table
Flowers | Decor at dining tables and all LCFM tables
Table settings | Plates, silverware, napkins, menus, glasses
Place menus and bundles very last**
Volunteer room | TY cards & gifts. Pizza and drinks all set
Drink tables | Prepping Wine, Beer, Coffee Tables
Coffee table

## Task List Night Of
Action | Done?

## Silent Auction Items
Item # | Auction Item Title | FMV | Starting Bid $ | Winning Bid | Paid? | Winner Name | Winner Phone | Winner Email/Contact | Item Donor Business | Donor Name | Donor Email | Donor Phone Number | Donor Mailing Address

## Donations Tracking
CCM Board Member | Thank You Sent? | first | last | amount | fund_code | address_1 | address_2 | city | state | zipcode | Use a Corporate Match? | Employer or Associated Business: | dedication_type | dedication_name | email | phone | country | Merged Doc ID - Auction Only Donation Receipts | Merged Doc URL - Auction Only Donation Receipts | Link to merged Doc - Auction Only Donation Receipts | Document Merge Status - Auction Only Donation Receipts | Merged Doc ID - GFF & Auction TY Letters | Merged Doc URL - GFF & Auction TY Letters | Link to merged Doc - GFF & Auction TY Letters | Document Merge Status - GFF & Auction TY Letters | Merged Doc ID - GFF Only 9/21/21 | Merged Doc URL - GFF Only 9/21/21 | Link to merged Doc - GFF Only 9/21/21 | Document Merge Status - GFF Only 9/21/21
|  | Online Donations | [23 empty] | 1eLpP6Aa9iGd11amipdSsj9UKLNVID0wmh0eGtZxN4Yk | https://docs.google.com/document/d/1eLpP6Aa9iGd11amipdSsj9UKLNVID0wmh0eGtZxN4Yk/edit?usp=drivesdk | Eric Stoll Good Farmer Fund Donation Receipt | Document successfully created; Document successfully merged; Manually run by leavenworthmarket@gmail.com; Timestamp: Sep 21 2021 4:15 PM
|  | Cash/Check Donations | [23 empty] | 1298rLh20RnAl2A3lu1Bzw4xKdpOu1OAlTR17Dr7IPj0 | https://docs.google.com/document/d/1298rLh20RnAl2A3lu1Bzw4xKdpOu1OAlTR17Dr7IPj0/edit?usp=drivesdk | Laura Keller Good Farmer Fund Donation Receipt | Document successfully created; Document successfully merged; Manually run by leavenworthmarket@gmail.com; Timestamp: Sep 21 2021 4:15 PM
| Total Direct Donations |  |  | 0
[18 empty] | 1B7vfQh8GY1qVlQ0Y5RQQRzVNDZQy0Zii0S-yT6-cKz0 | https://docs.google.com/document/d/1B7vfQh8GY1qVlQ0Y5RQQRzVNDZQy0Zii0S-yT6-cKz0/edit?usp=drivesdk | Terry and Aisha Houghton Farm to Table Auction Receipt | Document successfully created; Document successfully merged; Manually run by leavenworthmarket@gmail.com; Timestamp: Sep 21 2021 3:45 PM

## NVScriptsProperties (hidden)
autocratn | autocratp
dataSheetName | "Calendar"
v | "5.1"
dataSheetId | "3.01831007E8"
updateTime | "1.667960279616E12"
vp | "5.1"
ssId | "1mDIdy4ZuJZUpSPV5n2Bn8uMgtMDTh6iWwt9juvMMba8"

## Thank Yous Tracking
Thank you sent? | Category | Name | Donation | Mailing Address
Volunteers
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Special Event Support
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Hosts
FALSE
Chefs
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Sponsors
FALSE
FALSE
FALSE
FALSE
Photographer
FALSE
FALSE
FALSE | Direct Donors
FALSE | Auction Item Donors
FALSE | Auction Winners

## DO NOT DELETE - AutoCrat Job Se (hidden)
Job ID | Job Name | Template ID | Data Sheet ID | Header Row | First Data Row | File Name | File Type | Share As | Folders | Dynamic Folder Reference | Conditionals | Mode | Append Breaks | Tags | Run On Time Trigger | Time Trigger Frequency | Run On Form Trigger | Send Email And Share | Email To | Email CC | Email BCC | Email Reply To | Email No Reply | Email Subject | Email Body | Prevent Resharing | Time Trigger Timestamp | Form Trigger Timestamp
_1632253519012 | Auction Only Donation Receipts | 1UzBW3FS_e3uLQhsvGd8G_CXv_-xBhsarpFy-quAOt6I | 373792289 | 1 | 2 | <<First Name>> <<Last Name>> Farm to Table Auction Receipt | GOOG_DOC | EDITABLE | ["1UWf0zmCyWPPo6NmCU85dNb_C1oZxZ_ol"] | [] | [{"headerMap":"Category","value":"Auction Only"}] | MULTIPLE_OUTPUT | TRUE | [{"details":{"isUnmapped":false,"headerMap":"First Name"},"tag":"First Name","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"Last Name"},"tag":"Last Name","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"Auction Donation"},"tag":"Auction Donation","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"Auction Item"},"tag":"Auction Item","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"Item Value"},"tag":"Item Value","type":"STANDARD"}] | FALSE |  | FALSE | FALSE |  |  |  |  | FALSE |  |  | FALSE
_1632253809251 | GFF & Auction TY Letters | 1lt3_Y1teJ2tjBqHHfWvBrkeGEnrVbuxJTrg-sF1K-bs | 373792289 | 1 | 2 | <<First Name>> <<Last Name>> Farm to Table Donations Receipt | GOOG_DOC | EDITABLE | ["1fyfl2Fjxu-B-Mt-3PsRSzFSP2tFIeAmL"] | [] | [{"headerMap":"Category","value":"GFF & Auction"}] | MULTIPLE_OUTPUT | TRUE | [{"details":{"isUnmapped":false,"headerMap":"First Name"},"tag":"First Name","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"Last Name"},"tag":"Last Name","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"GFF Donation"},"tag":"GFF Donation","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"Auction Donation"},"tag":"Auction Donation","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"Auction Item"},"tag":"Auction Item","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"Item Value"},"tag":"Item Value","type":"STANDARD"}] | FALSE |  | FALSE | FALSE |  |  |  |  | FALSE |  |  | FALSE
_1632255267074 | GFF Only 9/21/21 | 1A-gF5oeSyZ38nZaG3TjZ_kYbOTOnZYL2rCSgkxOI2AQ | 373792289 | 1 | 2 | <<First Name>> <<Last Name>> Good Farmer Fund Donation Receipt | GOOG_DOC | EDITABLE | ["1eBGHWA7yndsKQ2uHu36SvNTYH8d6G2zh"] | [] | [{"headerMap":"Category","value":"GFF Only"}] | MULTIPLE_OUTPUT | TRUE | [{"details":{"isUnmapped":false,"headerMap":"First Name"},"tag":"First Name","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"Last Name"},"tag":"Last Name","type":"STANDARD"},{"details":{"isUnmapped":false,"headerMap":"GFF Donation"},"tag":"GFF Donation","type":"STANDARD"}] | FALSE |  | FALSE | FALSE |  |  |  |  | FALSE |  |  | FALSE