## Checklist Color
3-5 Months to Opening | Done? | Category | Tasks
|  | Governance | Set Annual Budget with the Board
|  | Governance | Create/Update Vendor Application + Rules
|  | Governance | Draft Job Descriptions (if hiring additional staff)
|  | Paperwork | Get Location Permitting in Order
|  | Paperwork | Submit all Food Access Applications
|  | Paperwork | Submit Annual Membership Forms for WSFMA
|  | Sponsorship | Set Sponsor Info Packet + Deadline
|  | Sponsorship | Make Sponsorship Asks
|  | Sponsorship | Public Call for Sponsors
|  | Sponsorship | Sponsor Invoices + Tracking
|  | Sponsorship | Thank your sponsors as they pay!
|  | Communication | Set Vendor Meeting Date
|  | Communication | Update Website with Opening Days & Vendor Rules/Application Details
|  | Logistics | Create a Music & Events Schedule (know how many hours of music are in your budget!)
|  | Logistics | Set a social media post schedule
|  | Logistics | Make a signage checklist - for at the market and for marketing the market!
|  | Logistics | Draft your site plan
|  | Logistics | Identify your ideal vendor balance
2 Months to Opening | Done? | Category | Tasks
|  | Governance | Post Open Jobs & Start Hiring Interviews
|  | Paperwork | Update or Get Insurance
|  | Paperwork | File Health Dept Paperwork
|  | Logistics | Equipment Inventory & Assess Needs
|  | Logistics | Do you have enough tokens??
|  | Governance | Run equipment budget by the board
|  | Logistics | Start buying any necessary new equipment!
|  | Logistics | Create music/entertainment application
|  | Communication | Post on Social Media to recruit musicians
|  | Communication | Announce Vendorship Meeting Time
|  | Communication | Draft your poster (Use design checklist from Kim Nelson & attend the graphic design class she is giving at the next Member Market Meeting!)
1.5 Months to Opening | Done? | Category | Tasks
|  | Governance | Start Checking Vendor Insurance
|  | Logistics | Plan a manager's week off in the middle of the season!?
|  | Logistics | Make a volunteer plan and sign-up form
|  | Logistics | Schedule Musicians as you go, get those opening weeks booked first if possible
|  | Communication | Announce Volunteer sign-ups
|  | Communication | Finalize & Print Posters!
1 Month to Opening | Done? | Category | Tasks
|  | Governance | Get additional staff's Time-Off Requests + Payroll Forms
|  | Sponsorship | Finalize Sponsor Banner design & Send to printers!
|  | Communication | Finalize any other signage & send to printers
|  | Communication | Set & share volunteer schedule
|  | Communication | Post Posters!
|  | Communication | Submit an announcement article to the local newspaper
|  | Logistics | Update & refill Manager Binder
|  | Logistics | Prep Volunteer timesheets
2-3 Weeks to Opening | Done? | Category | Tasks
|  | Logistics | Prep staff timesheets
|  | Logistics | Prep for vendor meeting
|  | Logsitics | Hold Vendor Meeting
|  | Communication | Communicate plans with volunteers
|  | Communication | Social media & email list reminders!
|  | Communication | Send volunteers details
1 Week to Opening
|  | Communication | Social media & email list reminders!
|  | Communication | Send first volunteer reminder email
|  | Communication | Send vendor reminder email (if applicable)
Opening Day

## Checklist B&W
3-5 Months to Opening | Done? | Category | Tasks
|  | Governance | Set Annual Budget with the Board
|  | Governance | Create/Update Vendor Application + Rules
|  | Governance | Draft Job Descriptions (if hiring additional staff)
|  | Paperwork | Get Location Permitting in Order
|  | Paperwork | Submit all Food Access Applications
|  | Paperwork | Submit Annual Membership Forms for WSFMA
|  | Sponsorship | Set Sponsor Info Packet + Deadline
|  | Sponsorship | Make Sponsorship Asks
|  | Sponsorship | Public Call for Sponsors
|  | Sponsorship | Sponsor Invoices + Tracking
|  | Sponsorship | Thank your sponsors as they pay!
|  | Communication | Set Vendor Meeting Date
|  | Communication | Update Website with Opening Days & Vendor Rules/Application Details
|  | Logistics | Create a Music & Events Schedule (know how many hours of music are in your budget!)
|  | Logistics | Set a social media post schedule
|  | Logistics | Make a signage checklist - for at the market and for marketing the market!
|  | Logistics | Draft your site plan
|  | Logistics | Identify your ideal vendor balance
2 Months to Opening | Done? | Category | Tasks
|  | Governance | Post Open Jobs & Start Hiring Interviews
|  | Paperwork | Update or Get Insurance
|  | Paperwork | File Health Dept Paperwork
|  | Logistics | Equipment Inventory & Assess Needs
|  | Logistics | Do you have enough tokens??
|  | Governance | Run equipment budget by the board
|  | Logistics | Start buying any necessary new equipment!
|  | Logistics | Create music/entertainment application
|  | Communication | Post on Social Media to recruit musicians
|  | Communication | Announce Vendorship Meeting Time
|  | Communication | Draft your poster (Use design checklist from Kim Nelson & attend the graphic design class she is giving at the next Member Market Meeting!)
1.5 Months to Opening | Done? | Category | Tasks
|  | Governance | Start Checking Vendor Insurance
|  | Logistics | Plan a manager's week off in the middle of the season!?
|  | Logistics | Make a volunteer plan and sign-up form
|  | Logistics | Schedule Musicians as you go, get those opening weeks booked first if possible
|  | Communication | Announce Volunteer sign-ups
|  | Communication | Finalize & Print Posters!
1 Month to Opening | Done? | Category | Tasks
|  | Governance | Get additional staff's Time-Off Requests + Payroll Forms
|  | Sponsorship | Finalize Sponsor Banner design & Send to printers!
|  | Communication | Finalize any other signage & send to printers
|  | Communication | Set & share volunteer schedule
|  | Communication | Post Posters!
|  | Communication | Submit an announcement article to the local newspaper
|  | Logistics | Update & refill Manager Binder
|  | Logistics | Prep Volunteer timesheets
2-3 Weeks to Opening | Done? | Category | Tasks
|  | Logistics | Prep staff timesheets
|  | Logistics | Prep for vendor meeting
|  | Logsitics | Hold Vendor Meeting
|  | Communication | Communicate plans with volunteers
|  | Communication | Social media & email list reminders!
|  | Communication | Send volunteers details
1 Week to Opening
|  | Communication | Social media & email list reminders!
|  | Communication | Send first volunteer reminder email
|  | Communication | Send vendor reminder email (if applicable)
Opening Day